## General Plan
|  | < | [9 empty] | Monitoring
ID | Task | Progress | Fase | Assigned person | APs | accumulated APs | Planned value | Accumulated planned value | Estimated cost (minutes) | Accumulated estimated cost | Planned due date | Earned APs | Accumulated earned APs | Cumulative earned value | APs in revision | Accumulated APs in revision | Accumulated value under review | Real cost (mins) | Accumulated real cost | Actual end date
Stage 1
| Iteration 1 |  |  |  |  | 0 |  | 0% |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
T3 | Create database | Complete | diseño | David | 3 | 3 | 9.677% | 9.677% | 770 | 770 | 2023-06-27 | 3 | 3 | 9.677% | 3 | 3 | 9.677% |  | 0 | 2023-06-27
11 | Architecture test | Complete | documentación | David | 5 | 8 | 16.13% | 25.81% | 908 | 1678 | 2023-06-27 | 5 | 8 | 16.13% | 5 | 8 | 25.81% |  | 0 | 2023-06-28
13 | Create repository | Complete | documentación | David | 1 | 9 | 3.226% | 29.03% | 120 | 1798 | 2023-06-27 | 1 | 9 | 3.226% | 1 | 9 | 29.03% |  | 0 | 2023-06-27
6 | Technology stack selection | Complete | documentación | David | 3 | 12 | 9.677% | 38.71% | 770 | 2568 | 2023-06-27 | 3 | 12 | 9.677% | 3 | 12 | 38.71% |  | 0 | 2023-06-27
1 | Architecture diagram | Complete | documentación | David | 2 | 14 | 6.452% | 45.16% | 410 | 2978 | 2023-06-27 | 2 | 14 | 6.452% | 2 | 14 | 45.16% |  | 0 | 2023-06-27 | Aps | Valor
3 | Deployment diagram | Complete | documentación | David | 1 | 15 | 3.226% | 48.39% | 120 | 3098 | 2023-06-27 | 1 | 15 | 3.226% | 1 | 15 | 48.39% |  | 0 | 2023-06-28 | 1 | 120
2 | Project configuration | Complete | diseño | David | 8 | 23 | 25.81% | 74.19% | 1470 | 4568 | 2023-06-27 | 8 | 23 | 25.81% | 8 | 23 | 74.19% |  | 0 | 2023-06-29 | 2 | 410
4 | Architecture configuration | Complete | analisis | David | 8 | 31 | 25.81% | 100% | 1470 | 6038 | 2023-06-27 | 8 | 31 | 25.81% | 8 | 31 | 100% |  | 0 | 2023-06-29 | 3 | 770
5 |  |  |  |  | 31 | [15 empty] | 5 | 908
T1 | Iteration 2 |  |  |  |  | 0 |  | 0% |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 8 | 1470
8 | Log in | In progress | Implementación | David | 8 | 8 | 27.59% | 27.59% | 1470 | 1470 | 2023-06-30 | 0 | 0 | 0% | 0 | 0 | 0% |  | 0 |  | 13 | 2370
7 | Browse products | In progress | analisis | David | 5 | 13 | 17.24% | 44.83% | 908 | 2378 | 2023-06-30 | 0 | 0 | 0% | 0 | 0 | 0% |  | 0
9 | See specific product | In progress | analisis | David | 8 | 21 | 27.59% | 72.41% | 1470 | 3848 | 2023-06-30 | 0 | 0 | 0% | 0 | 0 | 0% |  | 0
10 | Create admin | In progress | Implementación | David | 3 | 24 | 10.34% | 82.76% | 770 | 4618 | 2023-06-30 | 0 | 0 | 0% | 0 | 0 | 0% |  | 0
12 | Log out | In progress | analisis | David | 5 | 29 | 17.24% | 100% | 908 | 5526 | 2023-06-30 | 0 | 0 | 0% | 0 | 0 | 0% |  | 0
29
14 | Iteration 3 |  |  |  |  | 0 |  | 0% |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
15 | Create product | Upcoming |  | David | 3 | 3 | 8.108% | 8.108% | 770 | 770 | 2023-07-04 | 0 | 0 | 0% | 0 | 0 | 0% |  | 0
17 | Browse report | Upcoming |  | David | 5 | 8 | 13.51% | 21.62% | 908 | 1678 | 2023-07-04 | 0 | 0 | 0% | 0 | 0 | 0% |  | 0
18 | Delete product | Upcoming |  | David | 3 | 11 | 8.108% | 29.73% | 770 | 2448 | 2023-07-04 | 0 | 0 | 0% | 0 | 0 | 0% |  | 0
FT1 | Browse admin | Upcoming |  | David | 5 | 16 | 13.51% | 43.24% | 908 | 3356 | 2023-07-04 | 0 | 0 | 0% | 0 | 0 | 0% |  | 0
16 | Delete admin | Upcoming |  | David | 3 | 19 | 8.108% | 51.35% | 770 | 4126 | 2023-07-04 | 0 | 0 | 0% | 0 | 0 | 0% |  | 0
19 | Update product | Upcoming |  | David | 13 | 32 | 35.14% | 86.49% | 2370 | 6496 | 2023-07-04 | 0 | 0 | 0% | 0 | 0 | 0% |  | 0
20 | Update admin | Upcoming |  | David | 5 | 37 | 13.51% | 100% | 908 | 7404 | 2023-07-04 | 0 | 0 | 0% | 0 | 0 | 0% |  | 0
21 |  |  |  |  | 37
22
23
24
FT2
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
FT3

## Team capacity
Member | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Total
David | 0 | 8 | 4 | 8 | 8 | 8 | 8 | 44
0
0
0
0
0
0
0
50% of team capacity | 0 | 4 | 2 | 4 | 4 | 4 | 4 | 22
Total | 0 | 8 | 4 | 8 | 8 | 8 | 8 | 44
| 0 | 240 | 120 | 240 | 240 | 240 | 240

## Defect Log
ID | Defect name | Cost in minutes | Severity | Injection fase | Detection fase | Kind | Status |  | Injection | Detection
1 | Delete comments in Spanish | 15 | Cosmetic | Implementation | Implementation | UI | To do | Analisi | 0 | 0
2 | Connection failure with the database | 20 | Urgent | Implementation | Implementation | Segurity | Done | Design | 0 | 0
3 | Database outage |  | Emergency | Implementation | Implementation | Data | Done
4 | Outdated version for creating React application | 5 | Urgent | Implementation | Implementation | Version | Done | Implementation | 6 | 6
5 | Failed connection with Auth0 | 5 | Necessary | Implementation | Implementation | Version | Done | Test | 0 | 0
6 | Failures with React context for product and admin user hooks | 5 | Necessary | Implementation | Implementation | Bug | To do | Production | 0 | 0