## General Plan
|  | < | [9 empty] | Monitoring
ID | Task | Progress | Fase | Assigned person | APs | accumulated APs | Planned value | Accumulated planned value | Estimated cost (minutes) | Accumulated estimated cost | Planned due date | Earned APs | Accumulated earned APs | Cumulative earned value | APs in revision | Accumulated APs in revision | Accumulated value under review | Real cost (mins) | Accumulated real cost | Actual end date
Stage 1
| Iteration 1 |  |  |  |  | 0 |  | 0% |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
T3 | Create database | Complete | deploy | David | 3 | 3 | 9.677% | 9.677% | 770 | 770 | 2023-06-27 | 3 | 3 | 9.677% | 3 | 3 | 9.677% | 35 | 35 | 2023-06-27
11 | Architecture test | Complete | deploy | David | 5 | 8 | 16.13% | 25.81% | 908 | 1678 | 2023-06-27 | 5 | 8 | 16.13% | 5 | 8 | 25.81% | 120 | 155 | 2023-06-28
13 | Create repository | Complete | deploy | David | 1 | 9 | 3.226% | 29.03% | 120 | 1798 | 2023-06-27 | 1 | 9 | 3.226% | 1 | 9 | 29.03% | 10 | 165 | 2023-06-27
6 | Technology stack selection | Complete | deploy | David | 3 | 12 | 9.677% | 38.71% | 770 | 2568 | 2023-06-27 | 3 | 12 | 9.677% | 3 | 12 | 38.71% | 25 | 190 | 2023-06-27
1 | Architecture diagram | Complete | deploy | David | 2 | 14 | 6.452% | 45.16% | 410 | 2978 | 2023-06-27 | 2 | 14 | 6.452% | 2 | 14 | 45.16% | 15 | 205 | 2023-06-27 | Aps | Valor
3 | Deployment diagram | Complete | deploy | David | 1 | 15 | 3.226% | 48.39% | 120 | 3098 | 2023-06-27 | 1 | 15 | 3.226% | 1 | 15 | 48.39% | 25 | 230 | 2023-06-28 | 1 | 120
2 | Project configuration | Complete | deploy | David | 8 | 23 | 25.81% | 74.19% | 1470 | 4568 | 2023-06-27 | 8 | 23 | 25.81% | 8 | 23 | 74.19% | 30 | 260 | 2023-06-29 | 2 | 410
4 | Architecture configuration | Complete | deploy | David | 8 | 31 | 25.81% | 100% | 1470 | 6038 | 2023-06-27 | 8 | 31 | 25.81% | 8 | 31 | 100% | 180 | 440 | 2023-06-29 | 3 | 770
5 |  |  |  |  | 31 | [15 empty] | 5 | 908
T1 | Iteration 2 |  |  |  |  | 0 |  | 0% |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 8 | 1470
8 | Log in | Complete | deploy | David | 8 | 8 | 30.77% | 30.77% | 1470 | 1470 | 2023-06-30 | 8 | 8 | 30.77% | 8 | 8 | 30.77% | 120 | 120 | 2023-06-30 | 13 | 2370
7 | Browse products | Complete | deploy | David | 5 | 13 | 19.23% | 50% | 908 | 2378 | 2023-06-30 | 5 | 13 | 19.23% | 5 | 13 | 50% | 60 | 180 | 2023-07-03
9 | See specific product | Complete | deploy | David | 5 | 18 | 19.23% | 69.23% | 908 | 3286 | 2023-06-30 | 5 | 18 | 19.23% | 5 | 18 | 69.23% | 60 | 240 | 2023-07-03
10 | Create admin | Complete | deploy | David | 3 | 21 | 11.54% | 80.77% | 770 | 4056 | 2023-06-30 | 3 | 21 | 11.54% | 3 | 21 | 80.77% | 80 | 320 | 2023-07-03
12 | Log out | Complete | deploy | David | 5 | 26 | 19.23% | 100% | 908 | 4964 | 2023-06-30 | 5 | 26 | 19.23% | 5 | 26 | 100% | 60 | 380 | 2023-07-03
26
14 | Iteration 3 |  |  |  |  | 0 |  | 0% |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
15 | Create product | Complete | deploy | David | 3 | 3 | 8.824% | 8.824% | 770 | 770 | 2023-07-04 | 3 | 3 | 8.824% | 3 | 3 | 8.824% | 45 | 45 | 2023-07-04
| Add Report | Complete | deploy | David | 5 | 8 | 14.71% | 23.53% | 908 | 1678 | 2023-07-04 | 5 | 8 | 23.53% | 5 | 8 | 23.53% | 120 | 165 | 2023-07-04
17 | Browse report | Complete | deploy | David | 5 | 13 | 14.71% | 38.24% | 908 | 2586 | 2023-07-04 | 5 | 13 | 38.24% | 5 | 13 | 38.24% | 55 | 220 | 2023-07-04
18 | Delete product | Complete | deploy | David | 3 | 16 | 8.824% | 47.06% | 770 | 3356 | 2023-07-04 | 3 | 16 | 47.06% | 3 | 16 | 47.06% | 35 | 255 | 2023-07-04
FT1 | Browse admins | Complete | deploy | David | 5 | 21 | 14.71% | 61.76% | 908 | 4264 | 2023-07-04 | 5 | 21 | 61.76% | 5 | 21 | 61.76% | 60 | 315 | 2023-07-04
16 | Delete admin | Complete | deploy | David | 3 | 24 | 8.824% | 70.59% | 770 | 5034 | 2023-07-04 | 3 | 24 | 70.59% | 3 | 24 | 70.59% | 40 | 355 | 2023-07-04
19 | Update product | Complete | deploy | David | 5 | 29 | 14.71% | 85.29% | 908 | 5942 | 2023-07-04 | 5 | 29 | 85.29% | 5 | 29 | 85.29% | 70 | 425 | 2023-07-05
20 | Update admin | Complete | deploy | David | 5 | 34 | 14.71% | 100% | 908 | 6850 | 2023-07-04 | 5 | 34 | 100% | 5 | 34 | 100% | 80 | 505 | 2023-07-05
21 |  |  |  |  | 34
1
2
FT2
3
4
5
6
7
8
9
10
33
34
35
36
37
38
39
40
41
FT3

## Team capacity
Member | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Total
David | 8 | 8 | 4 | 8 | 8 | 8 | 8 | 52
0
0
0
0
0
0
0
50% of team capacity | 4 | 4 | 2 | 4 | 4 | 4 | 4 | 26
Total | 8 | 8 | 4 | 8 | 8 | 8 | 8 | 52
| 240 | 240 | 120 | 240 | 240 | 240 | 240

## Defect Log
ID | Defect name | Cost in minutes | Severity | Injection fase | Detection fase | Kind | Status |  | Injection | Detection
1 | Comments in Spanish | 20 | Cosmetic | Implementation | Test | UI | To do | Analisi | 0 | 0
2 | Connection failure with the database | 160 | Urgent | Analisis | Implementation | Segurity | Done | Design | 3 | 0
3 | Database outage | 120 | Emergency | Design | Implementation | Data | Done
4 | Outdated version for creating React application | 60 | Urgent | Design | Implementation | Version | Done | Implementation | 2 | 5
5 | Failed connection with Auth0 | 240 | Necessary | Analisis | Implementation | Version | Done | Test | 0 | 2
6 | Failures with React context for product and admin user hooks | 60 | Necessary | Design | Implementation | Bug | Done | Production | 0 | 0
7 | Lack of more comments to the code | 30 | Cosmetic | Implementation | Test | UI | To do
8